Salsabeel Finance App

Phase 1 Implementation Spec

For:	Implementation team / contractor
From:	Hadley
Date:	June 2026
Target go-live:	8 weeks from kickoff
Replaces:	Current static HTML dashboards + manual Excel workflow

# 1. Goal & Scope

Deliver a hosted, login-protected web app that lets Uzair (Finance Director) and Hadley access live Salsabeel TikTok Shop finance data, with three data sources:

- Xero — pulled automatically via API (already authorised via the dataSights connector).

- TikTok files — uploaded manually each month via a drag-and-drop UI.

- Stock & COGS — entered by Uzair via a web form (no more emailing xlsx files).

All three flow into a single Postgres database, which feeds the existing dashboards (replacing the inline JSON they currently use).

## 1.1 In scope

- Authentication (email + password, two roles: admin and finance).

- Xero API integration — auto-pull bank transactions + invoices nightly.

- TikTok file upload UI with file-type detection and validation.

- Stock & COGS web forms (add opening stock, add shipment, edit SKU).

- Dashboards (existing 4 HTML pages, wired to live API).

- Audit log (who uploaded what, who edited stock).

- Data freshness indicator on every dashboard.

## 1.2 Out of scope (deferred to Phase 2+)

- TikTok Shop API / Ads API (deferred until developer approval secured).

- LLM chatbot (Phase 3).

- Multi-tenant / multi-brand support.

- Email/Slack alerts (manual review for now).

- Mobile-optimised layout (desktop-first for MVP).

- Forecasting auto-refresh (forecast is recomputed on demand only).

# 2. Users & Roles

| Role | Granted to | Permissions |
| --- | --- | --- |
| admin | Hadley | Full access: view dashboards, upload files, edit stock/COGS, manage users, see audit log. |
| finance | Uzair | View dashboards, upload TikTok files, edit stock/COGS via forms. Cannot manage users. |
| viewer | Future: board / auditor | Read-only access to dashboards. No data modifications. Useful for monthly board pack share. |

Only admin and finance roles need to be implemented in Phase 1. Viewer role can be stub for Phase 2.

# 3. System Architecture

Five layers, deployed across three managed services. All hosting in EU/UK regions for GDPR.

| Layer | Technology | Host |
| --- | --- | --- |
| Frontend | Next.js 14 (React, TypeScript) | Vercel (UK/EU edge) |
| Backend API | FastAPI (Python 3.11) — reuses existing analytics scripts | Railway or Fly.io (London region) |
| Database | PostgreSQL 16 | Neon (EU-West) |
| Auth | Clerk (email + password, optional Google) | Clerk-hosted (~£25/mo) |
| File storage | S3-compatible object store | Cloudflare R2 (UK) |
| Xero connector | dataSights MCP (already set up) OR direct Xero OAuth | Same as today |
| Scheduler | Vercel Cron (Xero pull) + on-demand triggers | Vercel-hosted |
| Error tracking | Sentry | Sentry-hosted |

Estimated monthly hosting cost: £110-£140.

# 4. UI Pages

Seven pages total. Existing dashboards are re-used.

| Page | Function | Access |
| --- | --- | --- |
| /login | Clerk-hosted login. Email + password, optional Google. No self-signup. | Public |
| /dashboard | Landing page after login. Shows monthly dashboards menu, Quarterly Reports link, June Forecast link, data freshness indicators. | All roles |
| /dashboard/[month] | The existing monthly dashboards (March/April/May), wired to fetch live data from the API instead of inline JSON. | All roles |
| /data-sources | Drag-and-drop TikTok file upload. Shows Xero sync status. Lists last upload per file type with timestamp. | admin + finance |
| /stock | Stock register: every SKU with current qty, last shipment, last sale date. Add Shipment button. | admin + finance |
| /stock/sku/[sku] | Per-SKU detail: opening qty, all shipments (date, qty, cost/unit), edit form. Audit history. | admin + finance |
| /settings | User management (admin only). Audit log. | admin |

# 5. Data Sources

## 5.1 Xero — API pull (automated)

Source: Xero API via the existing dataSights connector OR a direct Xero OAuth integration (cleaner long-term). Recommendation: direct OAuth.

What to pull:

- Bank account transactions (the TIKTOK INFORMATION credits — for cash-basis settlement).

- Sales invoices to "TikTok" contact (the weekly INV-xxxx records).

- Chart of accounts (to map account codes to display names).

- Profit & Loss (used for cross-checks only, not as primary source).

Refresh: nightly cron at 03:00 UK time. Manual "Refresh now" button on /data-sources page.

Auth: Xero OAuth 2.0 — Hadley authorises Salsabeel's Xero org once during setup, tokens stored encrypted in DB.

## 5.2 TikTok — Manual file upload

Source: Uzair uploads files monthly via /data-sources page. Drag-and-drop or click-to-browse.

Supported file types (auto-detected from contents):

- TikTok Income / Payout (.xlsx) — single file per month with Reports / Statements / Order details / Payments / Fees explanation tabs.

- TikTok Ads — daily creative (.xlsx × 28-31 files) — or the monthly aggregate, both supported.

- TikTok Ads — campaign list / overview (.xlsx, optional).

- TikTok product analytics / shop overview (.xlsx, optional for GMV per SKU).

Validation on upload:

- File-type detection from contents (header row signature), not filename.

- Period detection from data (e.g., Reports tab "Time period: 2026/05/01-2026/05/31").

- Duplicate detection via SHA-256 hash of file contents.

- Statement-total check: sum of daily settlements must equal the Reports "Total settlement amount" within £0.01. Reject if mismatch.

- Date-range overlap: warn if uploading a file for a period that already has data — confirm before overwriting.

Storage: file uploaded to R2, parsed by backend, parsed JSON written to Postgres. Raw file retained 24 months for audit.

## 5.3 Stock & COGS — Web forms

Source: Uzair enters via a form on /stock. No more emailing Huzzy Stock spreadsheets.

Two forms:

Add Opening Stock (used once, at company onboarding or year-start):

- SKU code (autocomplete from existing SKUs, or "+ Add new SKU" flow).

- Quantity (integer, > 0).

- Landed cost per unit ex-VAT (decimal, > 0).

- As-of date (defaults to today).

Add Shipment (used as inbound stock lands):

- Shipment name (e.g., "Reef Air 3 - INV 18", free text).

- Landed date (date picker).

- Line items: for each, SKU + qty + landed cost per unit ex-VAT.

- Save adds these as new FIFO layers.

Add SKU (when new product is introduced):

- SKU code (unique, e.g., RP100050).

- Product name (free text).

- Optional: TikTok Shop product ID (for auto-matching).

- Optional: SKU family / brand (Reef / Nyla / etc).

Validation: SKU code uniqueness, qty/cost positive numbers, landed date not in future. All edits audit-logged.

# 6. Database Schema (Postgres)

Core tables. Indexes and foreign keys to be added by implementing team. All money in pence (BIGINT) to avoid float issues.

| Table | Key columns | Source |
| --- | --- | --- |
| users | id, email, role, clerk_user_id, created_at | Clerk webhook |
| skus | sku_code (PK), product_name, tiktok_product_id, brand, created_at | Form input |
| stock_layers | id, sku_code (FK), qty_in, qty_consumed, cost_per_unit_pence, landed_date, source (opening / shipment), shipment_name, audit_user_id, created_at | Form input |
| tiktok_uploads | id, file_hash, file_name, file_type (income / ads_daily / etc), period_start, period_end, r2_key, uploaded_by, uploaded_at, parse_status, parse_error | File upload |
| tiktok_statements | id, period_year, period_month, statement_date, statement_id, settle_amount_pence, net_sales_pence, fees_pence, shipping_pence, adjustments_pence, source_upload_id | Parsed from upload |
| tiktok_orders | id, period_year, period_month, order_id, statement_id, sku_code (FK), qty, gross_pence, net_pence, settle_pence, tt_commission_pence, aff_pence, ship_pence, etc. | Parsed from upload |
| tiktok_ads | id, period_year, period_month, date, campaign_id, sku_code (FK), spend_pence, revenue_pence, orders, source_upload_id | Parsed from upload |
| xero_bank_txns | id, date, description, reference, amount_pence, type (credit/debit), xero_invoice_number, last_synced_at | Xero API |
| xero_invoices | id, invoice_number, date, status, total_pence, paid_pence, payment_date, line_items_json, last_synced_at | Xero API |
| audit_log | id, user_id, action (uploaded_file / edited_sku / added_shipment / etc), resource_type, resource_id, payload_json, created_at | Backend |

# 7. Backend API Endpoints

All endpoints require auth (Clerk JWT in Authorization header). FastAPI generates OpenAPI docs at /docs automatically.

|  | Endpoint | Auth | Purpose |
| --- | --- | --- | --- |
| GET | /api/dashboards/:month | Any | Returns DATA payload for a given month dashboard (same JSON shape as today). |
| GET | /api/reports/quarterly | Any | Quarterly Reports data (Report 1 + Report 2 + reconciliation). |
| GET | /api/forecast/june | Any | Forecast data. Recomputed on each call from current DB state. |
| POST | /api/uploads/tiktok | admin+finance | Multipart file upload. Returns upload_id and parse status. |
| GET | /api/uploads | admin+finance | List of recent uploads with parse status, period covered. |
| GET | /api/stock | Any | Stock register: every SKU with current qty. |
| GET | /api/stock/:sku | Any | Single-SKU detail with full layer history. |
| POST | /api/stock/shipments | admin+finance | Add a new shipment (header + line items). |
| POST | /api/stock/opening | admin+finance | Add an opening stock entry for a SKU. |
| POST | /api/skus | admin+finance | Add a new SKU. |
| POST | /api/xero/sync | admin+finance | Manual trigger of Xero pull. Background job in production. |
| GET | /api/health | Public | Health check + data freshness summary. |
| GET | /api/audit-log | admin | Audit log with filters by user / action / date. |

# 8. Validation Rules

Kept deliberately simple for Phase 1 — catches obvious mistakes, not exhaustive.

### 8.1 File uploads

- Max file size 50 MB.

- Reject if file hash matches an existing upload.

- Reject if file type cannot be auto-detected.

- Warn (but allow with confirmation) if period overlaps with existing data.

- Reject income file if sum of daily statements ≠ Reports total within £0.01.

### 8.2 Stock & COGS forms

- SKU code: 3-30 chars, A-Z 0-9 _, unique.

- Quantity: positive integer.

- Cost per unit: positive decimal, max £1,000.

- Landed date: not in future, not more than 5 years ago.

- On edit: existing FIFO consumption preserved (cannot reduce qty below qty_consumed).

### 8.3 Xero sync

- Connection check on every sync — if Xero OAuth token expired, flag on /data-sources.

- Idempotent: re-running sync for the same period does not duplicate records (key on Xero invoice ID / bank txn ID).

# 9. Authentication

- Clerk-hosted login flow (no UI to build for Phase 1).

- Email + password. Optional Google sign-in for Hadley.

- No self-signup — Hadley invites users from /settings.

- Role stored in Clerk user metadata + mirrored in users table via webhook.

- Backend verifies Clerk JWT on every API call; role check on protected endpoints.

- Session timeout: 30 days (Clerk default).

- No password reset emails to build — Clerk handles it.

# 10. Deployment & DevOps

### 10.1 Environments

- production — salsabeel-finance.[domain], real data.

- staging — staging.salsabeel-finance.[domain], cloned data, used for testing before deploying to prod.

- Local dev environment using Docker Compose (Postgres + R2 mock).

### 10.2 CI/CD

- GitHub repo, main branch = staging, tagged releases = production.

- GitHub Actions for tests on every PR.

- Vercel auto-deploys frontend on push.

- Railway/Fly auto-deploys backend on push.

- DB migrations via Alembic (Python), run automatically on backend deploy.

### 10.3 Monitoring

- Sentry for backend + frontend errors.

- Vercel Analytics for frontend usage.

- Better Stack for uptime monitoring (Phase 2; for Phase 1 use Vercel built-in).

- Weekly automated backup of Postgres to R2.

# 11. Timeline (8 weeks)

| Week | Milestone | Detail |
| --- | --- | --- |
| 1 | Setup + auth | Repo, Vercel/Railway/Neon accounts, Clerk integration, login flow, role middleware. |
| 2 | Static deploy of existing dashboards | Lift existing 4 HTML dashboards into Next.js, behind login. Uzair has a working URL. |
| 3 | DB + Postgres schema | Apply schema migrations, seed with Mar/Apr/May data from existing JSON. |
| 4 | Backend API + dashboards wired | FastAPI service, /api/dashboards/:month endpoints, frontend fetches data instead of inline JSON. |
| 5 | TikTok file upload | /data-sources UI, file-type detection, parser (reuses existing scripts), validation gates, audit log. |
| 6 | Xero OAuth + sync | Direct Xero OAuth, nightly cron, manual refresh button. Bank transactions + invoices flowing. |
| 7 | Stock & COGS forms | /stock pages, opening stock form, shipment form, add SKU form, FIFO engine running off DB. |
| 8 | QA + go-live | End-to-end testing with Uzair, fix any data discrepancies, switch DNS to production, train Uzair. |

# 12. Acceptance Criteria for Go-Live

All must pass before switching off the static HTML / Excel workflow.

- Uzair can log in via email + password.

- Hadley can invite a new user from /settings.

- Uzair can upload a TikTok income .xlsx and see the corresponding monthly dashboard refresh within 60 seconds.

- Uzair can add a shipment via the form and see updated stock + COGS on the dashboards.

- Xero bank transactions show up on the bank-reconciliation card without manual intervention.

- All four dashboards (March / April / May / Quarterly Reports / June Forecast) work end-to-end against the API.

- Numbers reconcile to within £1 against the current static HTML for Mar/Apr/May data.

- Audit log records every upload and stock edit.

- Site loads in under 3 seconds for the dashboard page.

- Vercel and Railway/Fly deployments are working with auto-deploy from main branch.

# 13. Decisions Required Before Kickoff

- Domain name (e.g., salsabeel-finance.bloxgroup.co.uk).

- Who builds it: in-house, contractor, or continued iteration in Cowork.

- Confirm Xero connector approach: dataSights vs direct OAuth.

- Confirm Clerk acceptable for auth (alternative: Auth0, Supabase Auth — Clerk recommended for simplicity).

- Approve £110-£140/month hosting budget.

- Confirm GDPR / data residency requirement is UK/EU only.

# Appendix A — Reused Assets

The following existing assets become inputs to Phase 1, not throwaway:

- Python pipeline — ~2,000 lines of tested parsers, FIFO engine, ad attribution, forecast model. Becomes the backend services.

- Dashboard HTML/CSS — 4 dashboards in dark theme. Become Next.js components with fetch() in place of inline JSON.

- JSON schemas — master JSON per month, forecast payload, reports payload. Become the API response contracts (no shape change required).

- Excel templates — Salsabeel_Mar_May_2026_Reports.xlsx and Salsabeel_June_2026_Forecast.xlsx. Repurposed as "Export to Excel" feature on dashboards.

- Xero connector — dataSights MCP currently working. Either continue using it (call from FastAPI) or replace with direct OAuth (cleaner).

# Appendix B — Notes on Existing Data Quality

- Mar/Apr/May data is fully reconciled to the penny against TikTok statements and Xero bank. Migration can use existing JSON directly.

- Stock data is from Uzair's Huzzy Stock 2 file. Migration: import as opening stock + four shipments (Reef Air 2 06/04, Sea containers 10/04, Reef Air 1 01/05).

- A few small SKUs (RP150003, RP150006, RP150008, RP340031, RP375011) appear in shipments but not in the inventory directory — confirm names with Uzair during Week 7.

- Nyla family has documented stock-out at 31 May. Phase 1 must surface this on the dashboard.